## Sheet1
| main work | 2h weekly meeting |  | meeting result | separate work
week |  |  |  |  | Joy |  |  | Richa |  | Daniel |  | Anton |  |  | William
1 | group set up
2 | topics searching, finding datasets | topic discussion |  | three topics | Same about 5h per week |  |  | Same about 5h per week |  | Same about 5h per week |  | Same about 5h per week |  |  | Same about 5h per week
3 | finding datasets | topic discussion |  | graft plan | datasets search topic search |  |  | datasets search topic search |  | datasets search topic search |  | datasets search topic search |  |  | datasets search topic search
[5 empty] | Same about 10h per week |  |  | Same about 10h per week |  | Same about 10h per week |  | Same about 10h per week |  |  | Same about 10h per week
4 | write breif, summary ideas | summary ideas |  | breif | write breif |  |  | write breif |  | write breif |  | write breif |  |  | write breif
|  | look at datasets |  | graft plan | most of time for discussion |  |  | most of time for discussion |  | most of time for discussion |  | most of time for discussion |  |  | most of time for discussion
|  | write breif |  |  | Same about 8h per week |  |  | Same about 8h per week |  | Same about 8h per week |  | Same about 8h per week |  |  | Same about 8h per week
5 | clearing and editring topic, | topic discussion |  |  | more discusion after tutorial |  |  | more discusion after tutorial |  | more discusion after tutorial |  | more discusion after tutorial |  |  | more discusion after tutorial
|  | detail discussion |  | workload | think about new idea |  |  | think about new idea |  | think about new idea |  | think about new idea |  |  | think about new idea
6 | discussion about topic, define topic | topic discussion |  | feature decision | define topic, do research of tools |  |  | paper find |  | datasets search |  | paper find |  |  | datasets search
datasets find
7 | cleansing datasets | topic discussion |  | workload | cleaning two datasets |  |  | cleaning two datasets |  | cleaning six datasets |  | cleaning three datasets |  |  | cleaning four datasets
|  | cleaning merge discussion |  | topic clarify | scrapy two datasets
8 | normalization | summary datasets |  | normalization | 4 or 5 datasets for each people to normalize |  |  | 4 or 5 datasets for each people to normalize |  | 4 or 5 datasets for each people to normalize |  | 4 or 5 datasets for each people to normalize |  |  | 4 or 5 datasets for each people to normalize
|  | fix clearning problem |  | workload | some datasets are really complex |  |  | some datasets are really complex |  | some datasets are really complex |  | some datasets are really complex |  |  | some datasets are really complex
|  | future plan discussion |  |  | mongoDB learn |  | discussionwithDaniel | mongoDB learn |  | normalize function search | discussionwithJoy | normalize function search |  |  | mongoDB learn
9 | build database, do survey | planning | DB | DB sructure | DB | 6 hours extra lab work |  | DB | 6 hours extra lab work | survey design | 6 hours extra lab work | survey design | 6 hours extra lab work |  | DB | 6 hours extra lab work
|  | fix normalize problem |  | workload | merge function search |  |  | process data |  | process data |  | weather dataset | mergefunction search |  | process data
10 | build model, application | result of survey |  | application structure | feature selection model |  |  | draft report |  | survey analysis | draft report | feature selection model |  |  | application building - flask
| collect survey data | model |  | workload | survey analysis | [6 empty] | application building DB
[5 empty] | 5 hours extra lab work |  |  | 5 hours extra lab work |  | 5 hours extra lab work |  | 5 hours extra lab work |  |  | 5 hours extra lab work
11 | build model, application, survey analysis
12 | visualization and report
13
14
15 | presentation
more than 10 hours work (including 2 hours discussion)
about 10 hours work (including 2 hours discussion)
less than 10 hours work (including 2 hours discussion)